## For Dropdown (hidden)
Sub-Group | Division | Civil Contract | QPS Contract | QSS Team | AC Contract | RI Contract | IR Contract | Instrumentation Contract | Grading | Submission (Internal) | Submission (External) | Status | WSO Status | RFV Status | NC Status | Category of Concern | Category of Incident | Mosquito Breeding | Alert Level Category | Feedback Type | Feedback Issue Concerned | QSS Team | NCN Status | NCN Closed By | Prognosis | Updating Status | Risk of Delay | Reasons for Any Potential Delay | Overall Progress | Type of Infrastructure | Project Status | Stakeholder Engagement
CID(C1) | 1CIC(C1) | AM103 | AM1031 | QPS (Civil) | AM1063 | CQ21013 | SR22135 | AM1062 | Excellent | Prelim Architectural Drawing | BCA | Accepted with comments | Approved | Closed | Amicable Settlement / Commercial Settlement | Minor | Crime | Yes | Red | Feedback | Housekeeping | Senior Resident Engineer | Open | By LTA | Satisfactory | Pending Update | On Track | No Issues | Design | Covered Linkway | Design (Submission & Approval) | Advisor Engagement
CID(C2) | 1CIC(C2) | AM106 | AM1061 | QPS (Geo) | AC23086 | RI24123 | SR23088 | DE1512 | Good | Final Architectural Drawing | NEA | Approved | Cancelled | In Progress | Pending SO Decision | Moderate | Dangerous Incident | No | Yellow | Enquiry | Damage to Property | Resident Engineer | Closed | By QPS | Good | On-Going | At Risk | Site Constraints | Construction | L2P | Projects with BSC: Construction (Up to BSC)
RID(C1) | 1RC(C1) | AM110 | BD2011 | SRE | BD2013 |  | SR23109 |  | Satisfactory | Concept Design Submission | NParks | In progress | Closed |  | Pending Substantiation | Major | Dangerous Occurence (MOM Reportable) |  | Green | Request | Workmanship | RTO |  |  | NA | Updated | High Risk | Design Clearances | Completed | Bus Stop | Projects with BSC: Construction (After BSC)
RID(C2) | 1RC(C2) | AM201 | DE1171 | RE | CF101 |  | SR24029 |  | Unsatisfactory | AIP | PUB (Dra) | PJT Received | In Progress |  | Settled |  | Enviromental Harm/Infringement/Non-Compliance |  | No Cases | Appeal | Flooding / Ponding | QA/QC |  |  | Poor |  |  | Stakeholders Requirements |  | Cycling Path | Projects without BSC: Construction
RID(C3) | 1RC(C3) | AM202 | DE1511 | RTO | CF2013 |  | SR24079 |  |  | Prelim | PUB (Sew) | PJT Reverted | Issued |  | SO Decision Issued |  | Fire Occurence |  |  | Compliment | Hazards |  |  |  | Excellent |  |  | Service Diversions |  | Road | Defects Liability Period
| 2CIC(C1) | AM203 | DE1601 |  | CQ20115 |  | SR25007 |  |  | Pre-final | PUB | Rejected | Substantially Completed |  | Withdrawn |  | Near Miss |  |  | Suggestion | Signs | [6 empty] | Others |  | Bus Interchange | TOP Obtained
| 2CIC(C2) | AM205 | DE1701A |  | CQ21148 |  | SR25058 |  |  | Final | HDB | Submitted |  |  |  |  | Near Miss (PGI Hazard Hzard Classification "A") |  |  | Others | Alternate Route | [8 empty] | Bus Depot | CSC Obtained
| 2RC(C1) | BD201 | DE1761 |  | CR1013B | [5 empty] | TC | [5 empty] | Other Occurence |  |  |  | Environmental | [8 empty] | Others | Handing Over
| 2RC(C2) | BD202 | DE1781 |  | DE1513A | [5 empty] | LTA DBC (Roads) | [5 empty] | Damage to Property |  |  |  | Traffic | [9 empty] | CWW
| 2RC(C3) | CF201 | DE1821 |  | DE1513B | [5 empty] | LTA DBC (Rails) | [5 empty] | Road/Traffic Incident |  |  |  | Potholes | [9 empty] | FCC
| 3CIC(C1) | CF202A | DE1951 |  | DE1703 | [5 empty] | SLA | [5 empty] | Security Violation |  |  |  | Faulty Assets
| 3CIC(C2) | CF202B | RC2071 |  | DE1773 | [5 empty] | DSTA | [5 empty] | Damage to Utility |  |  |  | General Enquiry
| 3RC(C2) | CF205 |  |  | DE1773 | [5 empty] | URA | [5 empty] | Others |  |  |  | Others
|  | DE117 |  |  | DE1783 | [5 empty] | Others
|  | DE151 |  |  | DE1823
|  | DE160 |  |  | DE1953
|  | DE170 |  |  | RC2033
|  | DE176 |  |  | CF101-01
DE177
DE178
DE182
DE188
DE189
DE195
RC203
RC207
RC210
DE152
NEA
[10 empty] | 3R - No. of trees affected | No. of trees planted

## DE152 2.0
Contract DE152
1. Main Contract Information
Contract Number
Subgroup
Division
Contract title
Contractor
Contract Sum
Contract Commencement Date
Contract Completion Date
Extension of Time (EOT) Date
Project Lead
Project Officer
Project Team
Performance Grading
Project Status
2. Supporting Contracts (Qualified Person (Supervision))
Contract Number
Subgroup
Division
Contract title
Consultant
Contract Sum
Contract Commencement Date
Contract Completion Date
Officer in Charge
Officer in Charge Representative
Overall Company Performance Grading
No. of Near Miss Reported
2.1 QSS Team (QPS(Civil), QPS(Geo), RE, RTO, QAQC etc)
Name | Designation | Reg No. |  | Performance Rating | Remarks
eg. John | QPS (Civil) | PE-1234
eg. Wei Xuan |  | RE-1234
eg. Tan |  | RTO-1234
eg. Ang |  | RTO-ME1234
3. Supporting Contracts (Accredited Checker)
Contract Number
Subgroup
Division
Contract title
Consultant
Name of Accredited Checker
Contract Sum
Contract Commencement Date
Contract Completion Date
Officer in Charge
Officer in Charge Representative
Overall Company Performance Grading
Individual Performance Grading
4. Supporting Contracts (Registered Inspector)
Contract Number
Subgroup
Division
Contract title
Consultant
Contract Sum
Name of Registered Inspector (Archi)
Name of Registered Inspector (M&E)
Name of Registered Inspector (FSE)
Contract Commencement Date
Contract Completion Date
Officer in Charge
Officer in Charge Representative
Overall Company Performance Grading
Individual Performance Grading RI Archi
Individual Performance Grading RI M&E
Individual Performance Grading RI FSE
5. Supporting Contracts (Independent Reviewer)
Contract Number
Subgroup
Division
Contract title
Consultant
Contract Sum
Name of Independent Reviewer
Contract Commencement Date
Contract Completion Date
Officer in Charge
Officer in Charge Representative
Performance Grading
6. Supporting Contracts (Instrumentation)
Contract Number
Subgroup
Division
Contract title
Consultant
Name of Instrumentation Consultant
Contract Sum
Contract Commencement Date
Contract Completion Date
Officer in Charge
Officer in Charge Representative
Overall Company Performance Grading
Individual Performance Grading
7. Main Civil Scope of Works
1. One flyover across ECP from Xilin Ave to TMCR/ T5 2. One flyover across ECP, TMCR & Changi Airport Diversion Canal (CADC). 3. Two vehicular tunnels under cross CADC with adjoining depressed roads including a facility building (FB2), stormwater & wastewater pump sumps, pump rooms. 4. Vehicular underpass undercrossing slip road from Xilin Ave/ to ECP, ECP & slip road from TMCR with adjoining depressed road with a facility building (FB3). 5. Landscape structure for terrace planters at depressed road before tunnel including two other locations. 6. Four new vehicular bridges crossing CADC. 7. Widening/ deepened/ reconstruction of CADC. 8. Widening & realignment of Xilin Ave, ECP, TMCR, Changi Coast Walk, reconfiguration & enhancement works at existing Tanah Merah Flyover. 9. Design & modify an existing pedestrian underpass along ECP & ECP service Road into shared (pedestrian & cyclist) underpass, including covered staircase, covered ramps. 10. Utility Specific Ducts (USDs) 11. 1 rain shelter for motorists along ECP below proposed flyover towards T5. 12. New bus stops, walkways, shared paths & new cycling path. 13. Design & construct new sewers. 14. Earth retaining structures & slopes.
8. Key Achievements of the Month / Progress
1. Key Achievements 1 2. Key Achievements 2
9. Area of Concerns | Category of Concerns | Mitigation Measures
eg. Concern 1
eg. Concern 2
eg. Concern 3
10. Prognosis |  |  |  |  | Classification of Prognosis
eg. Works are on Schedule. Expected CWW to be on 01 October 2025
11. Design Submission Status
11.1 Internal
Location | Elements | Submission | Status | Submission date | Days lapse | Risk of Delay
11.2 External
Location | Elements | Submission | Status | Submission date | Days lapse | Risk of Delay
12. Construction Progress on Site
Location | Progress Update | Elements/ Coating | Total Quantity (per design) | Actual Completion | Percentage (%) | X Coordinate | Y Coordinate | Risk of Delay | Reasons for Any Potential Delay | Remarks for any potential delay
13. Expenditure/Claims/WSOs/RFVs/EOT
13.1 Work Service Orders (WSO) (Internal) | WSO Status | WSO Amount | Progress Payment | WSO Start Date | WSO End Date
|  | 999999 | 888888 | DD/MM/YYYY | DD/MM/YYYY
13.2 Work Service Orders (WSO) (External) | WSO Status | WSO Amount | Progress Payment | WSO Start Date | WSO End Date
|  | 999999 | 888888 | DD/MM/YYYY | DD/MM/YYYY
13.3 Progress Claim | Amount |  | Total Cumulative |  | Total Contract Sum
2025-01-01 | 50000 |  | 50000
2025-02-01 | 100000 |  | 150000
2025-03-01 | 500000000 |  | 650000000
2025-04-01 | 1000000000 |  | 1650000000
2025-05-01
2025-06-01
2025-07-01
2025-08-01
2025-09-01
13.4 Request For Variation (RFV) Title | RFV Amount | Variation Order (VO) Payment | Cumulative RFV Amount | RFV Status
eg. To provide additional benches for bus interchange | 150000 | 50000 | 150000
13.5 Notified Claim | NC Amount ($) | EOT (days) | Date of Claim | NC Status
eg. NC 001 - Notification of Delay in BCA Building Plan
eg. NC 002 - Notification of Claim for Extension of Time - Clementi Bus Interchange - New Provision of Solid Fire Partition Boards Above Fixed Glass Panels
eg. NC 003 - Notification of Intent to Claim for Extension of Time Review of Safety Bollard setting out at All 7 Bus Interchanges.
13.6 Extension Of Time (EOT) | WSO End Date | Actual Completion Date | EOT (Days) | Status
eg. W58 - Yishun Avenue 3 | 2024-01-08 | 2024-04-12 | 95
13.7 Non-Conformance Notices (NCN) Details | Status (Open / Closed) | Date Raised | Date Closed | NCN Issued By | Remarks
eg. Improper concrete mix ratio used in column casting e.g. Installation of water proofing materials that was not in accordance with approced M&W drawings
13.8 Non-Conformance Notices (NCN) Summary | No. of NCN Issued (Month) |  |  | Cumulative No. of NCN issued-to-date
2025-01-01
2025-02-01
2025-03-01
2025-04-01
2025-05-01
2025-06-01
2025-07-01
2025-08-01
2025-09-01
2025-10-01
2025-11-01
2025-12-01
14. Safety Performance
14.1 Utility Damage |  | Occurrence Date | Time Taken for Repair (hrs) | Affected Stakeholder | Repair Cost | X Coordinate | Y Coordinate
eg. On 17 March, contractor conducted a trial trench to locate a 75mm gas pipe which is not shown on the service plan, they locate the pipe and backfill the trench on the same day. No damage was observed, and no gas smell was detected at the time. On 21 March, SP Gas officer arrived on site after receiving feedback from nearby HDB Blk residents regarding gas disruption. SP Gas officer detected a possible gas leakage from the trial trench area. On 22 March, SP Gas repair team exposed the 75mm pipe and discovered a hole on it, the damaged section was replaced by SP and the area was backfilled on the same day. Investigation is still ongoing. |  | DD/MM/YYYY | 3.75 | SPPG | 5000
14.2 Non-MOM Reportable Incident |  |  | Occurrence Date | Category of Incident
eg. On 15 April, JL cables Detection was carrying out hacking and excavation of 2nd half of lane 2 of Loyang Avenue when banksman observed 3 out of 10 pipes were damaged. Upon investigation, the damaged pipes were Starhub cables and Starhub requested Contractor to provide new PVC pipe to wrap over the damaged pipe before carrying out repair works. |  |  | DD/MM/YYYY
14.3 MOM Reportable Accident (More than 3 days MC) |  |  | Occurrence Date | Mandays Lost
e.g. On 4 June, IP was assisting the prime mover driver in securing the load with a lever chain ratchet when he sustained finger injury. IP suffered a laceration on the tip of his finger and was given a 15 days MC from 4 to 18 June. |  |  | DD/MM/YYYY
14.4 MOM Reportable Accident (Less than 3 days MC) |  |  | Occurrence Date | Mandays Lost
e.g. On 10 August, a worker tripped over uneven ground and sustained a minor cut in his leg. He received outpatient treatment at a clinic and was given 3 days MC from 10 to 12 August. |  |  | DD/MM/YYYY
14.5 Environmental Infringement |  |  |  | Affected Stakeholder | Occurrence Date
NEA conducted a site visit to DE160 on 10 April 2025 and found mosquito larvae in a broken water-filled barrier (WFB) and an abandoned bicycle tyre at Tampines North work zone. A sample was taken to determine if it was Aedes. Subsequently, NEA issued a $3000 fine to contractor and the fine was paid up on 14 July 2025. |  |  |  | NEA
14.6 Near Misses (Category A) | Corrective Action Taken | Location | Work Activity | Type of Hazard | Direct/Root Causes
eg. Reported by SAE Kamarudin – It was observed that the GI pipes coupler was not covered and the coupler poses a risk of causing laceration to anyone passing by the barrier. | Immediate action was taken – The surpervisor and workers were called over to bring a new cover to be secured onto the coupler. | Bishan Road, near LP80 | Cycling Path Network | Laceration | Inadequate guarding/ protection
14.7 Vector Control (Location) | Inspection Date | Any Findings? | Actions Taken | Fines Issued | Category | X Coordinate | Y Coordinate
eg. Tuas Road, near LP80 | DD/MM/YYYY | Yes | (Details of Action Taken) | 2000
14.8 Summary of Planned General Inspection (PGI) |  |  | Number of Findings
Personal Protective Equipment
Excavation
Lifting Operation
Working on Height
Housekeeping
Traffic Control & Road Safety
Demolition
Electrical
Safe Means of Access
Piling
Falling Hazard
Prevention of Fire
First-Aid
Safe Place of Employment
Health Requirements
Storage of Petroleum and Flammable
Welding and Cutting Tools
Work in Confined Space
Noise Control
Earth Control Measures (ECM)
Prevention of Mosquito Breeding
Others
15. ESS Score
Month | Score
2025-01-01 | eg. 70.12
2025-02-01
2025-03-01
2025-04-01
2025-05-01
2025-05-01
2025-06-01
2025-07-01
2025-08-01
2025-09-01
2025-10-01
2025-11-01
2025-12-01
16. Overall Progress
Month | Early (%) | Late (%) | Actual (%) | Early Variance (Weeks) | Late Variance (Weeks)
2025-01-01
2025-02-01
2025-03-01
2025-04-01
2025-05-01
2025-06-01
2025-07-01
2025-08-01
2025-09-01
2025-10-01
2025-11-01
2025-12-01
17. Timeline
17.1 High Risk Activities | Start Date | End Date | Type of Activity | X Coordinate | Y Coordinate
eg. PSPC Beam Launching | 2025-01-12 | 2025-01-12 | PSPC Beam Launching | 1.3657 | 103.9528
17.2 Commitment | Type of Infrastructure | Advisor | Priority Constituency Request (PCR) | GRC/SMC | Committed Date | Risk of Delay | Reasons for Any Potential Delay | Remarks for any potential delay | Overall Progress | X Coordinate | Y Coordinate
(Location)
17.3 Event | Start Date | End Date | Type of Activity | X Coordinate | Y Coordinate
17.4 Feedback | Location | Date received | Date closed | Type of Feedback | Issue Concerned
e.g. MOP received feedback on traffic congestion due to lane closures along Upper Changi Road North/East leading and TPE/SLE due to MR02 viaduct works from 11.30pm to 5am. e.g. MOP feedback that he noticed the trenching works was carried out close to a big tree. MOP raised concerns on the construction impact and health of the tree.
17.5 Road / Lane Closure (LTOC) (Details / Description) | Location | From (Date) | From (Time) | To (Date) | To (Time)
eg. Launching of high covered linkway roof launching works | Closure of Woodlands Crescent Road (in front of Admiralty Secondary School) | DD/MM/YYYY | 1:00 | DD/MM/YYYY | 4:30
18. Other Matters - Manpower
18.1 Manhours | Total Manhours |  | Cumulative Manhours
2025-01-01
2025-02-01
2025-03-01
2025-04-01
2025-05-01
2025-06-01
2025-07-01
2025-08-01
2025-09-01
2025-10-01
2025-11-01
2025-12-01
18.2. Manpower Forecast Reporting
Period | No. of Workers Currently Working |  | Forecasted Manpower Reporting
Q3 2025
Q4 2025
Q1 2026
Q2 2026
Q3 2026
Q4 2026
19. Other Matters - Eg. Green Initiatives/3R
19.1 Green Initiatives | Amount (Unit)
CMC (m3)
GFRP (kg)
Synthetic FRC (m3)
19.2 3R Initiative | Rehome |  |  | Repurpose |  |  |  | Recycle | 3R - No. of trees affected | No. of trees planted
Month | Girth < 1m | Girth > 1m | Total Rehomed | Girth < 1m | Girth > 1m | Total no. of trees specified in Contract to be repurposed | Total Repurposed | Total Recycled | Cumulative | Cumulative
2025-01-01 | A | B | A+B=C | D | E | F | D+E=G | H | C+G+H
2025-02-01
2025-03-01
2025-04-01
2025-05-01
2025-06-01
2025-07-01
2025-08-01
2025-09-01
2025-10-01
2025-11-01
2025-12-01